## What
Lesson Learned
Project Name: ________ Line Transfer Launch
Y's (WHATs)
| 1 | Factors to Evaluate
| 2 | Significance (Severity/Effect)
| 3 | Applicability (local vs. Global)
| 4 | Affects Product Design
| 5 | Design rules not existing or not followed
| 6 | Affects Process Design
| 7 | Work Instruction not existing / not followed
| 8 | Lack of Skills/Knowledge within ALV
| 9 | Supplier Capability is too low
2024

## How-LL
Lesson Learned
Project Name: ________ Line Transfer Launch
No./Tab | Lesson learned Description | LL Deployment | LL Deployment Owner |  | Region/Functional Area Found
|  |  |  | PM | SAP | Mfg Eng. | Prod. Eng. | Supply Chain | Procurement | Production | 1st Plant | New Plant
LL1 | All data was assumed current- obsolences existed in the master data transfer on finished goods part numbers. | Collect latest current models finsihed goods file. Flag obsolete part numbers for deletion/inactive. |  |  | x
LL2 | Change in supplier of rings after data transfer- was not known until late in project | Collect all change notices completed and in-process and ensure all are 100% processed in all dept changes. |  |  | x | x | x |  | x
LL3 | SAP SLOCS and Types were not available or suitable for the program from existing conditions. | Define and follow SLOC and Type process flow early with all materials moved into correct SLOCS. |  |  | x
LL4 | Personnel not understanding SLOC and Bin configuration | Make simple 1-pager showing flow and process of the SLOCS, Types, and Bins. |  |  | x |  |  | x
LL5 | Lack of Materials available for run-off of sub assemblies | Plan run-off and confirm direct materials by manual inventory for sub assemblies. | [5 empty] | x | x
LL6 | New part numbers required for outsourced materials. | Identify any outsourced or changed processes and identify list of materials requiring new part numbers for PLM/Team Center process early. Housing is changing-Outsource. |  |  | x | x | x | x | x
LL7 | Work center setup (cell arrangements) in some cases are not compatible with Dispatch setup. | Map and Compare layout of 1st plant equipment to identify differences in new plant and assign new Work Centers are required to have a concise mapping for production flow. |  |  | x | x |  |  |  |  | x
LL8 | Lap and center grinding process in routings no longer in practice or required. | Collect process flow of valid requirements from MFg Eng at 1st plant, check current process for 'skip-steps' |  |  |  | x |  |  |  |  | x
LL9 | 0peration not appearing and or combined with other operation step. | Ensure all actual practice steps are appearing in the routings of the parts, validation by Mfg Eng at 1st plant. |  |  | x | x
LL10 | Machines missing some or not able to perform with test programs on EOL. | Ensure all necessary programs and parameters are avialable in EOL. |  |  |  | x |  |  |  |  | x
LL11 | Maintenance training did not occur effectively while SMEs were on site at new plant. | Deploy training matrix early for training of maintenance personnel at new plant. | [8 empty] | x | x
LL12 | Suppliers hesitant and severely delayed in purchasing raw materials. | Submit LOI early, source with forecasts, and verify supplier's tier 2 PO's for raw materials. | [5 empty] | x | x
LL13 | Supplier did not understand capability of available equipment. | In case of equipment transfer or new asset installation ensure supplier has all details on the asset and understands the current process. |  |  |  | x |  |  | x
LL14 | Suppliers overselling or not validating capacity on existing equipment. | Deploy capacity planning sheet with assets, cycle times, and demonstrated quantitative analysis. | [5 empty] | x
LL15 | Cutting tooling showing early wear deterioration and failure without replacement. | Ensure consumable cutting tooling is available for replacement on installed equipment. |  |  |  | x |  |  |  |  | x
LL16 | Packing instructions not visible or in full detail to production. | Ensure final pack process instructions and materials are available. |  |  | x | x |  |  |  |  | x | x
LL17 | Currogate supplier late request and implementation of new label packaging. | Early engagement of currogated supplier for labeled packaging sizes and first articles. | [5 empty] | x | x
LL18 | Lack of bridge inventory to support production during asset moves. | Part-number-level Ramp-Up plan per asset to ensure coverage for production at both 1st and New plant. | [5 empty] | x |  |  | x | x
LL19 | Assets de-commissioned weeks early from 1st plant risking production stoppage. | Ensure alignment between Gantts of all work streams to ensure asset and ramp plans are keenly aligned and that all decommission points are stakeholder engaged decision nodes. |  |  |  | x |  | x |  |  |  | x
LL20 | Lack of clarity on actual units of past due, final alignment was all open orders requested. | Obtain clear quantitative data on all orders not fufilled on request date. | [5 empty] | x |  |  | x
LL21 | When ready to ramp up production at new plant, often only 1 operator was trained and either not present or otherwise engaged. | Ensure training matrix is robust- consider 3x3x3 model or similar. Compass matrix. | [7 empty] | x
LL22 | In some cases quality document for 1st pc inspection was missing or Work Order to document alignment on part number was incorrect. | Ensure through consolidated gantt and MOC actions that quality documents are available for production start-up. |  |  |  | x |  |  |  | x
LL23 | Printing output conditions were confusing and out of order in relation to material physical locations and end user work areas. | Ensure at master data SLOC/Type assignemnt that printer output conditions are correctly aligned and that printer requirements are collected from the end users. |  |  | x |  |  | x
LL24 | Not having BOMs for outsourced materials | Ensure BOM's are priority for release to vendors along with drawings. |  |  | x |  |  | x
LL25 | Cycle time per routings not available for costing | Ensure cycle times per operation are corrected per 1st plant baseline. |  |  | x | x
LL26 | Lack of clarify on owners for certain work stream outputs | Create responsibility matrix for S10 |  | x | [7 empty] | x
LL27 | Lack of complete planning for asset moves | Process- oriented planning for move . Racks, Matierals flow, etc. |  | x |  | x
LL28 | Lack of cross-functional involvement on operational agreements, esp operators and production. | Work Place Integration - all functions and levels are engaged in the operational sign-off. |  | x |  | x
LL29 | Difference in suppliers and active materials. | Compare lists of current suppliers and active materials from 1st plant and new plant. | [6 empty] | x
LL30 | Not utilizing training package early in the project | Ensure training packages are available and utilize internally early in the project |  | x | [5 empty] | x
LL31 | No thorough plan for part flow to assembly | Make plan-for-every-part on assembly and sub-assembly processes. |  | x |  |  |  | x
LL32 | Toubleshooting guide not avialable for product. | Minimum trouble-shooting guide for units, PFMEA preferred. |  |  |  | x
2024

## LL4
Lesson Learned
Project Name: ________ Line Transfer Launch
Lesson Learned Description:
Received from: |  | Received from:
Problem | Solution | Problem | Solution
Problem Statement/Description | Solution Statement/Description | Problem Statement/Description | Solution Statement/Description
Personnel not understanding SLOC and Bin configuration | Layout with process points, printers, SLOCS, and Types to understand correct flow of information and materials. |  | Inspection process: ICA: PCA:
Root Cause |  | Root Cause
lack of visual for knowledge transfer
Supporting -Sketches, Pictures, related Documents etc | Supporting -Sketches, Pictures, related Documents etc | Supporting -Sketches, Pictures, related Documents etc | Supporting -Sketches, Pictures, related Documents etc
Received from: |  | Received from:
Problem | Solution | Problem | Solution
Problem Statement/Description | Solution Statement/Description | Problem Statement/Description | Solution Statement/Description
| Inspection process: ICA: PCA: |  | Inspection process: ICA: PCA:
Root Cause |  | Root Cause
Improper grounding of testers
Supporting -Sketches, Pictures, related Documents etc | Supporting -Sketches, Pictures, related Documents etc | Supporting -Sketches, Pictures, related Documents etc | Supporting -Sketches, Pictures, related Documents etc
Roll-out Lesson Learnt
Problem |  | Solution
Problem Statement/Description |  | Solution Statement/Description
Inspection process: ICA: PCA:
Root Cause
Improper grounding of testers
Supporting -Sketches, Pictures, related Documents etc |  | Supporting -Sketches, Pictures, related Documents etc
LL Index

## LL6
Lesson Learned
Project Name: ________ Line Transfer Launch
Lesson Learned Description:
Received from: |  | Received from:
Problem | Solution | Problem | Solution
Problem Statement/Description | Solution Statement/Description | Problem Statement/Description | Solution Statement/Description
New part numbers required for outsourced materials. | Creation of new part numbers, drawings, and routings to support new process |  | Inspection process: ICA: PCA:
Root Cause |  | Root Cause
Material demand and consumption different from 1st plant process.
Supporting -Sketches, Pictures, related Documents etc | Supporting -Sketches, Pictures, related Documents etc | Supporting -Sketches, Pictures, related Documents etc | Supporting -Sketches, Pictures, related Documents etc
Received from: |  | Received from:
Problem | Solution | Problem | Solution
Problem Statement/Description | Solution Statement/Description | Problem Statement/Description | Solution Statement/Description
| Inspection process: ICA: PCA: |  | Inspection process: ICA: PCA:
Root Cause |  | Root Cause
Supporting -Sketches, Pictures, related Documents etc | Supporting -Sketches, Pictures, related Documents etc | Supporting -Sketches, Pictures, related Documents etc | Supporting -Sketches, Pictures, related Documents etc
Roll-out Lesson Learnt
Problem |  | Solution
Problem Statement/Description |  | Solution Statement/Description
Inspection process: ICA: PCA:
Root Cause
Supporting -Sketches, Pictures, related Documents etc |  | Supporting -Sketches, Pictures, related Documents etc
LL Index