## Sheet1
FMEA Matrix Toolkit
Process Step / Item | Potential Failure Mode | Potential Effect(s) of Failure | Severity (S) | Potential Cause(s) of Failure | Occurrence (O) | Current Controls | Detection (D) | RPN (Risk Priority Number) | Recommended Action | Responsibility | Completion Date | Action Taken | New RPN
Assembly of Component A | Loose or Misaligned Assembly | Product malfunction; poor quality | 8 | Incorrect torque applied during assembly | 5 | Manual inspection | 7 | 280 | Implement automated torque control | Quality Engineer | 2024-10-15 | Automated torque control installed | 56
Packaging Process | Incorrect Labeling | Wrong product shipped to customer | 6 | Human error during labeling process | 4 | Visual label check | 6 | 144 | Implement barcode scanning system | Operations Manager | 2024-11-01 | Barcode system in place | 24
Welding Process | Incomplete Welds | Product weakens and fails | 9 | Insufficient welding heat | 3 | Operator checks welds visually | 5 | 135 | Introduce automated ultrasonic weld testing | Welding Supervisor | 2024-12-01 | Ultrasonic testing system in place | 27
Product Inspection | Missed Defective Units | Defective product reaches customer | 10 | Inadequate testing parameters | 2 | Final visual inspection | 4 | 80 | Enhance testing procedures with automated sensors | Quality Assurance | 2024-10-25 | Sensors added to testing | 16